## Risk Register
Enterprise Risk Register
Project: Password Security & Exposure Remediation
Risk ID | Asset / Process | Threat / Vulnerability Description | Inherent Likelihood (1-5) | Inherent Impact (1-5) | Inherent Risk Score | Framework Mapping | Proposed Mitigation Controls | Residual Likelihood (1-5) | Residual Impact (1-5) | Residual Risk Score
RSK-002 | Corporate Workstations & Physical Facilities | Employees physically record passwords on sticky notes, desks, or underneath keyboards due to password fatigue. This introduces unauthorized physical credential theft, loss of confidentiality, and bypasses logical access controls. | 4 | 3 | 12 | ISO 27001:2022: A.8.1 (User Endpoint Devices), A.7.14 (Secure Working Areas) SOC 2: CC6.1 (Logical Access), CC6.3 (Physical Security) NIST SP 800-53: IA-5 (Authenticator Management), PE-3 (Physical Access Control) | 1. Technical: Deploy an Enterprise Password Manager (EPM) with centralized SSO integration to eliminate password fatigue. 2. Technical: Transition to passwordless authentication mechanisms (FIDO2 keys / Windows Hello for Business) where structurally feasible. 3. Governance: Implement mandatory quarterly 'Clean Desk & Clear Screen' physical security workplace sweeps alongside HR-driven accountability models. | 1 | 3 | 3

## Audit Plan
Compliance Control Validation & Audit Plan
Control ID | Audit Activity / Test Objective | Evidence To Collect | Frequency | Target Metric / KPI
AUD-003.1 | Conduct unannounced monthly after-hours 'Clean Desk' inspections of global physical corporate offices and regional facilities to identify exposed credentials on physical mediums. | Physical security sweep exception logs, compliance scorecards, and incident tracking records. | Monthly | 0 exposed corporate passwords or MFA backup materials discovered.
AUD-003.2 | Review Enterprise Password Manager (EPM) provisioning, activation, and usage telemetry data across user corporate profiles to evaluate operational adoption. | EPM administrative platform console exports, license allocation summaries, and identity directory reports. | Monthly | >98% active corporate user utilization and vault generation.
AUD-003.3 | Analyze historical regulatory onboarding training files to ensure completion of mandatory credential infrastructure and security hygiene coursework. | Learning Management System (LMS) completion certificates, training logs, and non-compliance escalation records. | Quarterly | 100% training completion rate across active workplace personnel.

## Corporate Policy
Corporate Policy Template - Password Security & Clean Desk
Document Reference: PL-SEC-005 ¦ Version: 1.0
1.0 Purpose | This policy defines explicit requirements for securing user credentials and mitigating physical threat vectors. It eliminates vulnerabilities tied to visible password disclosure within company spaces.
2.0 Scope | This policy governs all organizational personnel, global corporate facilities, remote workstations, and external workforce entities executing operations using company infrastructure.
3.0 Mandatory Controls
3.1 Clean Desk & Clear Screen Standard | Workforce members must ensure no clear-text credentials, physical sticky notes, whiteboards, or secondary multi-factor authentication (MFA) backup mechanics are left visible or exposed at any facility desk, terminal, or asset layout.
3.2 Prohibited Physical & Unencrypted Storage | Recording authenticators on physical materials or inside unencrypted local text documents (e.g., Notepad, Excel files) is strictly barred. All corporate authentications must reside exclusively inside the authorized Enterprise Password Manager (EPM).
4.0 Enforcement | Observed workspace exceptions, deliberate masking of authentication risks, or refusal to follow structural access workflows will trigger mandatory governance retraining, administrative privilege revocations, or progressive disciplinary reviews overseen by Human Resources.